## RAID LOG
| RAID Log | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[9 empty] | Risk | 4 | 0 | 2 | 0 | 0 | 0
| Project title: | Secure Authentication System with Encryption and Access Control |  | Project Id: | IP-11352 | Project Manager: | Harshada Topale |  | Assumption | 2 | 0 | 0 | 0 | 2 | 0
[9 empty] | Issue | 2 | 0 | 0 | 0 | 1 | 0
| DOCUMENT VERSION: | 1.0 |  | Last Updated date: | 30-05-2026 | Project Team Lead: | Dolly Panghate |  | Dependency | 2 | 0 | 0 | 0 | 1 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  | 10 |  |  |  |  | 6
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | OTP is simulated on-screen instead of being sent via real email/SMS, risking exposure in insecure environments. | Sensitive OTP could be viewed by unauthorized persons, undermining multi-factor authentication. | Restrict application access to trusted local environments during development; plan SMTP integration for production. | Dolly Panghate | High | 6 | Open
2 | Risk | HTTPS not enforced in the local XAMPP environment, leaving data in transit potentially unencrypted. | User credentials and session data could be intercepted via man-in-the-middle attacks. | Document this as a known constraint; enforce HTTPS via SSL certificate during production deployment. | Dolly Panghate | High | 6 | Open
3 | Risk | Brute-force login attacks could be attempted to gain unauthorized access to user accounts. | Account compromise leading to unauthorized access to sensitive user data. | Implemented login attempt limiting and session lockout after repeated failures. | Dolly Panghate | Moderate | 4 | Closed
4 | Risk | SQL Injection vulnerability if database queries are not properly parameterised. | Unauthorized access to or manipulation of database records. | Used prepared statements and parameterised queries throughout the PHP backend. | Dolly Panghate | High | 6 | Closed
5 | Assumption | Users will access the application via a secure, trusted browser environment. | If users access from unsecured devices, session and credential data may be at risk. | Communicate security best practices to users; plan for HTTPS in production. | Dolly Panghate | Low | N/A | Open
6 | Assumption | Database server and server-level security are managed by the hosting environment. | If server security is misconfigured, the application data may be exposed. | Verify server-level security settings before deployment; use XAMPP securely in development. | Dolly Panghate | Low | N/A | Open
7 | Issue | Real OTP delivery via email/SMS is not achievable within current project scope and tools. | OTP verification cannot be tested in a real-world scenario during the project period. | OTP is displayed on-screen as a simulation; noted as a deviation in the project report. | Dolly Panghate | Moderate | N/A | Closed
8 | Issue | Password reset / forgot password functionality is not implemented in the current version. | Users who forget their password have no self-service recovery option. | Noted as future scope; admin can manually reset passwords via the admin dashboard. | Dolly Panghate | Low | N/A | Open
9 | Dependency | Project depends on XAMPP being correctly configured with Apache, MySQL, and PHP on the local machine. | If XAMPP is not configured correctly, the entire application will fail to run. | Verified XAMPP installation and configuration at project start; documented setup steps. | Dolly Panghate | High | N/A | Closed
10 | Dependency | Weekly project reviews depend on Zoom meeting availability and Project Manager's schedule. | Delayed feedback or approvals if meetings are missed or rescheduled. | Meetings scheduled every Friday; agenda shared in advance to ensure productive sessions. | Harshada Topale | Low | N/A | Open
11
12
13
14
15
16
17
18
19
20
21
22
23
24