## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Cyber Security
INTERN NAME: | Bhoomi Dembani
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2026-04-30
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | Protecting Sensitive Data with Encryption and Access Control
PROJECT ID | IP-11352
INTERN NAME | Dolly Panghate
PROJECT MANAGER | Harshada Topale
INTRODUCTION
This Test Plan outlines the testing strategy, scope, methodology, and schedule for the 'Protecting Sensitive Data with Encryption and Access Control' project developed as part of the IAC Cyber Security Live Project (IP-11352). The system is a PHP-based secure web authentication application built on XAMPP (Apache, MySQL, PHP). It implements user registration and login with AES-128-CBC email encryption, bcrypt password hashing, OTP-based multi-factor authentication, role-based access control (RBAC), CSRF protection, brute-force login prevention, and a full activity logging system. Testing will focus on verifying that all security mechanisms function correctly, user data is protected, and access controls are properly enforced. Manual functional testing, security testing, and negative testing will be used to validate the system against the requirements defined in the SRS.
SCOPE
IN SCOPE
• User Registration: Input validation, bcrypt password hashing, AES-128-CBC email encryption, duplicate email detection • User Login: Credential verification, session creation, brute-force lockout after 5 failed attempts • OTP Authentication: OTP generation, on-screen display, 5-minute expiry, single-use enforcement, invalid OTP rejection • Role-Based Access Control: Admin and User role enforcement; server-side access checks on all protected pages • CSRF Protection: Token generation and validation on all form submissions • Session Management: Secure session lifecycle, session timeout, and logout • Activity Logging: Recording login and logout events with username and timestamp • Admin Dashboard: View all registered users, view activity logs • SQL Injection Prevention: Validated through PDO prepared statements • AES Encryption/Decryption: Verified for correctness in storage and retrieval
OUT OF SCOPE
• Real email delivery for OTP (OTP is simulated on-screen in the local environment) • Mobile application or native app testing • HTTPS/SSL certificate testing (local XAMPP environment does not use HTTPS) • Biometric or hardware-based authentication • Performance or load testing • Cross-browser compatibility testing beyond manual spot-checks • Automated test scripts or automation tools • Third-party payment or external API integrations
QUALITY OBJECTIVE
• Ensure all functional requirements defined in the SRS are met and verified through test execution • Confirm that all security mechanisms (encryption, hashing, OTP, RBAC, CSRF, brute-force protection) function correctly • Ensure no critical or high-severity bugs remain unresolved before final submission • Validate that sensitive user data (email, password) is never stored in plaintext • Verify that role-based access control prevents unauthorised access to admin pages • Ensure activity logging captures all required events accurately • Achieve 100% test case execution with all test cases achieving PASSED status
ROLES AND RESPONSIBILITIES
• Intern / Developer / Tester – Dolly Panghate: Responsible for designing, developing, and manually executing all test cases; documenting results in the Traceability Matrix; reporting and fixing all identified bugs • Project Manager – Harshada Topale: Reviewing test progress during weekly Friday Zoom meetings; approving test completion and project deliverables • Organisation – Cloud Counselage Pvt. Ltd.: Project sponsor; oversees quality standards and final deliverable acceptance
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
A Waterfall methodology is adopted for this project due to its short 6-week timeline (15 April – 30 May 2026) and clearly defined sequential phases: Requirement Gathering → Planning → Design → Development → Testing → Closure. Testing is conducted in the final phase after all development is complete. This approach is suitable for a single-intern project with well-defined requirements and no iterative scope changes.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
The following testing types are applied to the system: • Functional Testing: Verifies all features work as per the SRS (registration, login, OTP, RBAC, logging, admin dashboard) • Negative Testing: Tests system behaviour with invalid, missing, or malformed inputs to ensure proper error handling • Security Testing: Tests against common web vulnerabilities including SQL injection, CSRF attacks, brute-force login, and unauthorised direct URL access • Integration Testing: Verifies correct interaction between PHP modules, MySQL database, and session management components
BUG TRIAGE
Bugs are classified and resolved based on the following priority levels: • Critical (Priority 1): Security vulnerabilities (e.g. SQL injection, CSRF bypass, plaintext password storage) – must be fixed immediately before any further testing • High (Priority 2): Core functionality failures (e.g. login not working, OTP not generating, RBAC not enforcing) – must be fixed before test completion • Medium (Priority 3): Non-critical functional issues (e.g. incorrect error messages, UI layout issues) – fixed within the same development cycle • Low (Priority 4): Minor cosmetic issues – logged and addressed if time permits All bugs are fixed by Bhoomi Dembani and re-tested before marking test cases as PASSED.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Testing is deemed complete when all of the following criteria are met: • 100% of planned test cases have been executed • All 25 test cases in the Requirement Traceability Matrix show PASSED status • No Critical or High priority bugs remain open • All security test cases (SQL injection, CSRF, brute-force, RBAC bypass) have passed • Activity logging, encryption, and session management verified end-to-end • Test results reviewed and acknowledged by Project Manager Harshada Topale
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
The following test artifacts are delivered as part of this project: • Test Plan (this document) • Requirement Traceability Matrix (RTM) – with 25 test cases, expected/actual results, and PASSED/FAILED status • Software Design Specification (SDS) • Project Report – includes testing summary and results • Lessons Learnt Log – includes lessons from the testing phase
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
• Manual Testing: Primary testing method; all test cases executed manually by the intern • Browser DevTools (Chrome): Used to inspect HTTP requests, session cookies, and verify CSRF tokens • phpMyAdmin: Used to verify database state (encrypted emails, hashed passwords, activity log entries) • XAMPP Control Panel: Used to manage Apache and MySQL services during testing • Notepad++ / VS Code: Used to review and debug PHP source code during bug fixing
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Hardware: • Laptop/Desktop with minimum 4GB RAM, Windows 10/11 Software: • XAMPP (Apache 2.4 + PHP 8.x + MySQL 8.x) – Local development and testing server • PHP 8.x – Server-side application language • MySQL 8.x – Database for users, OTP, and activity log storage • Google Chrome / Mozilla Firefox – Browser for UI and functional testing • phpMyAdmin – Database administration and verification • Windows 10/11 – Operating system
ADDITIONAL COMMENTS
• All testing was conducted in a local XAMPP environment; HTTPS was not enforced as this is a local development setup • OTP delivery via real email (e.g. SMTP/Twilio) is out of scope; OTP was simulated on-screen for testing purposes • All 25 test cases were executed by Dolly Panghate between 20 May 2026 and 25 May 2026 • Weekly project progress was reviewed with Project Manager Harshada Topale every Friday via Zoom
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
User Registration Module | Test user registration with valid data, duplicate email, and weak password inputs | 2026-05-20 | 2026-05-20 | Dolly Panghate | Completed | All 3 test cases passed
User Login Module | Test login with valid credentials, invalid password, and non-existent email | 2026-05-20 | 2026-05-21 | Dolly Panghate | Completed | All 3 test cases passed
Brute Force Protection | Test account lockout after 5 consecutive failed login attempts | 2026-05-21 | 2026-05-21 | Dolly Panghate | Completed | Lockout triggered correctly
OTP Authentication | Test OTP generation, valid OTP entry, expired OTP, invalid OTP, and single-use enforcement | 2026-05-21 | 2026-05-22 | Dolly Panghate | Completed | All 5 OTP test cases passed
Role-Based Access Control | Test admin login, regular user login, and unauthorised admin page access via direct URL | 2026-05-22 | 2026-05-22 | Dolly Panghate | Completed | All 3 RBAC cases passed
CSRF Protection | Test form submission with valid CSRF token and with missing/tampered CSRF token | 2026-05-22 | 2026-05-23 | Dolly Panghate | Completed | Both CSRF cases passed
Session Management | Test session lifecycle on logout – session destroyed, access to dashboard redirects to login | 2026-05-23 | 2026-05-23 | Dolly Panghate | Completed | Session cleared correctly
Activity Logging | Test that login and logout events are correctly recorded in activity log table | 2026-05-23 | 2026-05-24 | Dolly Panghate | Completed | Both log events verified
SQL Injection Prevention | Test login form with SQL injection payload; verify PDO prepared statements block the attack | 2026-05-24 | 2026-05-24 | Dolly Panghate | Completed | Injection blocked; PASSED
AES Encryption Verification | Verify email stored as AES-128-CBC ciphertext and decrypts correctly on retrieval | 2026-05-24 | 2026-05-24 | Dolly Panghate | Completed | Encryption/decryption verified
Bcrypt Hash Verification | Verify password stored as bcrypt hash; password_verify() confirms correct match | 2026-05-24 | 2026-05-25 | Dolly Panghate | Completed | Hash verified in phpMyAdmin
Admin Dashboard | Test admin view of all users and activity logs; verify correct data display with decrypted emails | 2026-05-25 | 2026-05-25 | Dolly Panghate | Completed | Admin dashboard fully verified
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.