## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Cyber Security
INTERN NAME: | Bhoomi Dembani
PROJECT NAME: | Protecting Sensitive Data with Encryption and Access Control
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 30 April 2026
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Secure Authentication System with Encryption and Access Control
PROJECT ID | IP-11352
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 15-04-2026 | Importance of Data Security: Learned how encryption protects sensitive user data from unauthorised access. Implementing AES-128-CBC encryption for email storage and bcrypt for password hashing reinforced why plaintext storage is a critical vulnerability. | Security | No | Always encrypt sensitive data at rest using industry-standard algorithms. Never store passwords in plaintext. | Applied AES-128-CBC encryption for email fields and bcrypt hashing for all passwords in the authentication system. | Dolly Panghate | Solved | This was one of the most fundamental lessons of the project — data security must be built in from the design stage, not added later.
2 | 17-04-2026 | Understanding Encryption Algorithms: Gained in-depth knowledge of symmetric encryption (AES-CBC mode), IV generation, base64 encoding, and key management in PHP using openssl_encrypt() and openssl_decrypt(). | Technical / Encryption | No | Allocate dedicated research time before implementing any cryptographic module. Test encryption and decryption in isolation before integrating. | Studied PHP OpenSSL documentation, implemented and tested AES-128-CBC encryption module independently before integrating into the registration system. | Dolly Panghate | Solved | Skill gained: Practical understanding of symmetric encryption, IV handling, padding schemes, and secure key storage applicable to real-world systems.
3 | 22-04-2026 | Error Handling in Security Modules: Learned to manage invalid keys, decryption failures, and file/session handling errors properly. Initial AES decryption was returning garbled output due to incorrect IV handling. | Technical / Development | Yes – garbled decryption output observed during early testing. | Always test encryption and decryption together using known test values immediately after implementation. | Debugged the encryption key and IV handling; rewrote the module with proper padding and base64 encoding. Added error handling for decryption failures. | Dolly Panghate | Solved | This highlighted the importance of unit testing each security module individually before integration into the main system.
4 | 29-04-2026 | Project Planning and Phase Management: Understood how to divide the project into clear phases (Requirement Gathering, Planning, Design, Development, Testing, Closure) for better time management and delivery. | Project Management | No | Use a structured WBS and project schedule from day one. Breaking work into weekly sprints makes progress measurable and manageable. | Created a detailed WBS, Project Charter, and 6-week Project Schedule that guided all development activities from 15 April to 30 May 2026. | Dolly Panghate | Solved | Weekly Friday Zoom reviews with the Project Manager kept the project on track and allowed early course corrections throughout the timeline.
5 | 06-05-2026 | Testing and Debugging Security Features: Improved debugging skills while testing authentication modules — including login brute-force protection, OTP expiry, role-based access, and CSRF token validation. | Technical / Testing | Yes – regular user was able to access /admin/dashboard.php directly during early testing. | Define test cases for both happy path and attack scenarios before testing begins. Include negative test cases for all security features. | Created a manual test checklist covering registration, login, OTP authentication, RBAC, session management, and activity logging. All tests passed before final submission. | Dolly Panghate | Solved | Testing revealed the missing admin access control check — fixing it reinforced that server-side role verification must be present on every protected page.
6 | 13-05-2026 | User Interface Design for Security Systems: Learned to create a simple, browser-based, user-friendly interface for secure operations including registration, login, OTP entry, and admin dashboard — using HTML5 and CSS3. | Technical / UI Design | No | Keep the UI clean and intuitive even for security-critical flows. Error messages should be informative but must not reveal sensitive system details. | Designed responsive HTML/CSS forms for registration, login, and OTP verification. Admin dashboard displays user records and activity logs clearly. | Dolly Panghate | Solved | A well-designed UI reduces user errors during authentication and improves the overall security posture by guiding users through the correct flow.
7 | 20-05-2026 | Documentation Skills: Improved technical documentation and report writing skills through completing the SRS, Project Charter, RAID Log, WBS, Lessons Learnt Log, and the full Project Report. | Documentation | No | Maintain documentation in parallel with development — do not leave it all for the end. Each completed phase should be documented immediately. | Completed all 8 project deliverables systematically — SRS and Charter in Week 1-2, RAID Log and WBS in Week 2, and final Project Report in Week 6. | Dolly Panghate | Solved | Maintaining living documentation throughout the project made the final report much easier to compile and ensured no details were missed.
8 | 25-05-2026 | Understanding Access Control and Privilege Management: Gained practical understanding of Role-Based Access Control (RBAC) — ensuring Admin and User roles are enforced server-side on every protected page, not just at login. | Technical / Access Control | No – identified proactively during code review. | Enforce role checks at the top of every protected PHP file. Never rely on client-side redirection or session checks at login alone. | Added server-side role verification block to all admin pages. Non-admin users are redirected with an alert message if they attempt direct URL access. | Dolly Panghate | Solved | Technical understanding gained: Security must be layered — login check, session check, and page-level role check are each individually necessary and not interchangeable.