## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Program 2026 - Cybersecurity Project Schedule
|  | PROJECT START DATE | 2026-04-15 | 2026-04-15
|  | Display Week Sr No | 1 | [10 empty] | 2026-04-13 | [6 empty] | 2026-04-20 | [6 empty] | 2026-04-27 | [6 empty] | 2026-05-04 | [6 empty] | 2026-05-11 | [6 empty] | 2026-05-18 | [6 empty] | 2026-05-25 | [6 empty] | 2026-06-01 | [6 empty] | 2026-06-08
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2026-04-13 to 2026-06-14
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2026-04-13 to 2026-06-14
1 | Week 1-2: Initiation & Requirements (15-Apr to 25-Apr)
1.1 |  | Requirement Gathering |  |  |  | Dolly Panghate | 2026-04-15 | 2026-04-18 | 2026-04-18 | 8 | COMPLETED | 100%
1.1.1 |  | Requirement Gathering | Study problem statement and cybersecurity domain |  |  | Dolly Panghate | 2026-04-15 | 2026-04-16 | 2026-04-16 | 4 | COMPLETED | 100%
1.1.2 |  | Requirement Gathering | Complete Requirement Elicitation Questionnaire |  | 1.1.1 | Dolly Panghate | 2026-04-17 | 2026-04-18 | 2026-04-18 | 4 | COMPLETED | 100%
1.2 |  | Project Initiation |  |  |  | Dolly Panghate | 2026-04-19 | 2026-04-25 | 2026-04-25 | 10 | COMPLETED | 100%
1.2.1 |  | Project Initiation | Complete Project Charter |  | 1.1 | Dolly Panghate | 2026-04-19 | 2026-04-21 | 2026-04-21 | 4 | COMPLETED | 100%
1.2.2 |  | Project Initiation | Complete Software Requirement Specification (SRS) |  | 1.1 | Dolly Panghate | 2026-04-22 | 2026-04-25 | 2026-04-25 | 6 | COMPLETED | 100%
2 | Week 3: Planning (26-Apr to 02-May) |  |  |  |  | Dolly Panghate
2.1 |  | Project Planning |  |  |  | Dolly Panghate | 2026-04-26 | 2026-05-02 | 2026-05-02 | 12 | COMPLETED | 100%
2.1.1 |  | Project Planning | Create Work Breakdown Structure (WBS) |  | 1.2 | Dolly Panghate | 2026-04-26 | 2026-04-28 | 2026-04-28 | 4 | COMPLETED | 100%
2.1.2 |  | Project Planning | Create Project Schedule |  | 2.1.1 | Dolly Panghate | 2026-04-29 | 2026-04-30 | 2026-04-30 | 4 | COMPLETED | 100%
2.1.3 |  | Project Planning | Complete RAID Log (Risks, Assumptions, Issues, Dependencies) |  | 2.1.1 | Dolly Panghate | 2026-05-01 | 2026-05-02 | 2026-05-02 | 4 | COMPLETED | 100%
3 | Week 4: Design (03-May to 08-May) |  |  |  |  | Dolly Panghate
3.1 |  | System Design |  |  |  | Dolly Panghate | 2026-05-03 | 2026-05-08 | 2026-05-08 | 14 | COMPLETED | 100%
3.1.1 |  | System Design | Design RBAC roles and permissions matrix |  | 1.2.2 | Dolly Panghate | 2026-05-03 | 2026-05-04 | 2026-05-04 | 4 | COMPLETED | 100%
3.1.2 |  | System Design | Design encryption module architecture (AES-256, RSA-2048, Key Rotation) |  | 1.2.2 | Dolly Panghate | 2026-05-05 | 2026-05-06 | 2026-05-06 | 4 | COMPLETED | 100%
3.1.3 |  | System Design | Design MFA flow, Audit Log schema, IDS rules, Data Classifier patterns |  | 3.1.1 | Dolly Panghate | 2026-05-07 | 2026-05-08 | 2026-05-08 | 6 | COMPLETED | 100%
4 | Week 5-6: Development (09-May to 20-May) |  |  |  |  | Dolly Panghate
4.1 |  | Module Development | encryption.py — AES-256-CBC, RSA-2048, Key Rotation Manager |  | 3.1 | Dolly Panghate | 2026-05-09 | 2026-05-11 | 2026-05-11 | 10 | COMPLETED | 100%
4.2 |  | Module Development | access_control.py — RBAC, TOTP MFA, AuthManager, UserStore |  | 4.1 | Dolly Panghate | 2026-05-12 | 2026-05-14 | 2026-05-14 | 10 | COMPLETED | 100%
4.3 |  | Module Development | monitoring.py — AuditLogger (hash-chain), IDS, VulnerabilityScanner |  | 4.2 | Dolly Panghate | 2026-05-15 | 2026-05-17 | 2026-05-17 | 10 | COMPLETED | 100%
4.4 |  | Module Development | data_classifier.py — PII patterns (11 types), classifier, redactor |  | 4.2 | Dolly Panghate | 2026-05-17 | 2026-05-18 | 2026-05-18 | 6 | COMPLETED | 100%
4.5 |  | Module Development | app.py — Flask REST API (20+ endpoints), session management, integration |  | 4.1,4.2,4.3,4.4 | Dolly Panghate | 2026-05-18 | 2026-05-19 | 2026-05-19 | 8 | COMPLETED | 100%
4.6 |  | Module Development | index.html — Web dashboard UI (single-page, all modules) |  | 4.5 | Dolly Panghate | 2026-05-19 | 2026-05-20 | 2026-05-20 | 8 | COMPLETED | 100%
5 | Week 7: Testing (21-May to 25-May) |  |  |  |  | Dolly Panghate
5.1 |  | Testing | Functional testing of all encryption endpoints |  | 4.1 | Dolly Panghate | 2026-05-21 | 2026-05-22 | 2026-05-22 | 6 | COMPLETED | 100%
5.2 |  | Testing | Functional testing of RBAC, MFA, and authentication flow |  | 4.2 | Dolly Panghate | 2026-05-22 | 2026-05-23 | 2026-05-23 | 6 | COMPLETED | 100%
5.3 |  | Testing | Functional testing of IDS, Audit Log, Vulnerability Scanner, Data Classifier |  | 4.3,4.4 | Dolly Panghate | 2026-05-23 | 2026-05-24 | 2026-05-24 | 6 | COMPLETED | 100%
5.4 |  | Testing | End-to-end UI testing of web dashboard |  | 4.6 | Dolly Panghate | 2026-05-24 | 2026-05-25 | 2026-05-25 | 4 | COMPLETED | 100%
6 | Week 8: Deployment & Closure (26-May to 30-May) |  |  |  |  | Dolly Panghate
6.1 |  | Deployment | Local deployment — Flask app running at http://127.0.0.1:5000 |  | 5.4 | Dolly Panghate | 2026-05-26 | 2026-05-27 | 2026-05-27 | 4 | COMPLETED | 100%
6.2 |  | Project Closure | Complete Lessons Learnt Log |  | 5.4 | Dolly Panghate | 2026-05-27 | 2026-05-28 | 2026-05-28 | 4 | COMPLETED | 100%
6.3 |  | Project Closure | Complete Project Report |  | 6.2 | Dolly Panghate | 2026-05-28 | 2026-05-29 | 2026-05-29 | 6 | COMPLETED | 100%
6.4 |  | Project Closure | Final review and submission of all deliverables |  | 6.3 | Dolly Panghate | 2026-05-29 | 2026-05-30 | 2026-05-30 | 4 | COMPLETED | 100%

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1