## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Secure Authentication System with Encryption and Access Control
PROJECT SPONSOR | Cloud Counselage Pvt. Ltd.
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 15-04-2026
EXPECTED COMPLETION DATE | 30-05-2026
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To design and implement a secure web-based authentication system that protects sensitive user data using encryption techniques and access control mechanisms. The system will ensure secure credential storage using hashing and encryption, along with OTP-based multi-factor authentication to enhance security.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | With increasing cyber threats including data breaches and unauthorised access, Cloud Counselage Pvt. Ltd. requires a robust authentication system to protect sensitive user data within the Industry Academia Community (IAC). The system provides a cost-effective, scalable solution using industry-standard security practices such as AES encryption, password hashing, role-based access control, and session management — reducing the risk of data compromise and unauthorised access significantly.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Goal: Deliver a fully functional secure authentication system by 30-05-2026. Performance Goal: Zero critical security vulnerabilities in the final build. Time Goal: Complete all phases within the 15 Apr – 30 May 2026 timeline. Resource Goal: Single developer (Dolly Panghate) using open-source tools (XAMPP, PHP, MySQL, VS Code). Metrics: Successful OTP authentication, role-based access enforcement, encrypted data storage, and login activity logging.
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Secure user registration and login system with encrypted credentials 2. AES-128-CBC encrypted email storage and bcrypt password hashing 3. OTP-based multi-factor authentication module 4. Role-based access control (Admin and User roles) 5. Admin dashboard for user and log management 6. Login/logout activity logging system 7. Session management with secure headers and CSRF protection 8. Project Report, RAID Log, WBS, Lessons Learnt Log, and SRS documentation
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | - User registration with encrypted credentials - Secure login system with password hashing (bcrypt) - AES-128-CBC encryption for sensitive data (email) - OTP-based multi-factor authentication (simulated) - Role-based access control (Admin and User) - Admin dashboard for monitoring users and activity logs - Session management and secure HTTP headers - CSRF protection - Login and logout activity logging - MySQL database for data storage - PHP backend with XAMPP local server
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | - Real email/SMS-based OTP delivery (simulated only in this project) - HTTPS enforcement in production environment - Mobile application interface - Biometric authentication - Password reset / forgot password functionality - Cloud deployment - Integration with third-party identity providers (e.g. OAuth, Google SSO)
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Developer: Dolly Panghate (Project Implementer) Project Manager: Harshada Topale Project Sponsor: Cloud Counselage Pvt. Ltd.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | - XAMPP (Local server environment) - VS Code (Code editor) - Web browser (Testing and debugging) - MySQL Workbench (Database management) - Zoom (Weekly meetings with Project Manager)
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | N.A. – This is an academic internship project with no direct financial cost allocation.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd.
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.)
END CUSTOMER (Mention the client name.) | Industry Academia Community (IAC) – Cloud Counselage Pvt. Ltd.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | 1. OTP simulation risk: OTP is displayed on-screen rather than sent via email/SMS — risk of insecure exposure. Mitigation: Restrict to trusted testing environments; integrate real email service in future. 2. Brute-force attack risk: Repeated login attempts could compromise accounts. Mitigation: Implemented limited login attempts and session lockout. 3. SQL Injection risk: Improper database queries could expose data. Mitigation: Used prepared statements and parameterised queries. 4. Session hijacking risk: Weak session handling may lead to unauthorised access. Mitigation: Implemented secure session headers, session expiry, and CSRF tokens.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | - The system assumes users access the application via a secure environment (HTTPS recommended for production). - OTP delivery is simulated for the scope of this project; real delivery assumed in production. - Database security and server-level protection are managed by the hosting environment. - Users are assumed to have basic internet access and a modern web browser. - The project is assumed to be for academic/internship purposes with no real financial transactions.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.)
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 04-22-2026
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 04-29-2026
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 05-06-2026
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 05-20-2026
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 05-25-2026
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 05-28-2026
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 05-30-2026